## Product Backlog
Planned Sprint | Actual Sprint | Z-ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | Z-4-5 | As a developer, set up the project environment and integrate Groq API | MUST HAVE | Groq | Thumma Joseph Kumar | 3- Completed
S1 | S1 | Z-4-5 | As a developer, connect to AstraDB and store compliance data in vector form | MUST HAVE | AstraDB | Thumma Joseph Kumar | 3- Completed
S2 | S2 | Z-4-5 | As a user, upload a contract and get GDPR/DPDPA compliance analysis | MUST HAVE | GDPR/DPDPA | Thumma Joseph Kumar | 3- Completed
S2 | S2 | Z-4-5 | As a developer, store contracts in AstraDB with owner details | MUST HAVE | No Dependency | Thumma Joseph Kumar | 3- Completed
S3 | S3 | Z-4-5 | As a user, received updated contract with no regulatory risk | MUST HAVE | No Dependency | Thumma Joseph Kumar | 3- Completed
S3 | S3 | Z-4-5 | As a developer, update contracts when new regulatory amendments are released | SHOULD HAVE | No Dependency | Thumma Joseph Kumar | 3- Completed
S4 | S4 | Z-4-5 | As a developer, automate alert sending via SMTP when a contract is revised | SHOULD HAVE | SMTP setup | Thumma Joseph Kumar | 3- Completed
S4 | S4 | Z-4-5 | As a system, I setup a chatbot for each contracts | SHOULD HAVE | No Dependency | Thumma Joseph Kumar | 3- Completed
S4 | S4 | Z-4-5 | As a user, I received the revised contract with changes details | MUST HAVE | No Dependency | Thumma Joseph Kumar | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
Z-ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 81 | 17 | 16 | 13 | 13 | 13 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Z-4-5 | T1-01 | Set up Python virtual environment and install dependencies | 2025-10-16 | 2025-10-17 | Thumma Joseph Kumar | Build | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-02 | Integrate Groq API and test LLM response | 2025-10-18 | 2025-10-20 | Thumma Joseph Kumar | Coding | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-03 | Set up AstraDB connection and test connectivity | 2025-10-21 | 2025-10-31 | Thumma Joseph Kumar | Integration Test | 3- Completed | 9 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T1-04 | Create vector embedding pipeline using LangChain | 2025-11-01 | 2025-11-04 | Thumma Joseph Kumar | Coding | 3- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-01 | Upload GDPR and DPDPA Regulatories | 2025-11-05 | 2025-11-06 | Thumma Joseph Kumar | Others | 3- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-02 | Perform comprehensive compliance analysis on user contract | 2025-11-07 | 2025-11-09 | Thumma Joseph Kumar | Others | 3- Completed | 10 | 1 | 2 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-03 | Update contract if needed updation | 2025-11-10 | 2025-11-10 | Thumma Joseph Kumar | Others | 3- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T2-04 | Display interactive charts based on Analysis | 2025-11-11 | 2025-11-12 | Thumma Joseph Kumar | Others | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T3-01 | Track latest regulatory updates | 2025-11-13 | 2025-11-19 | Thumma Joseph Kumar | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T3-02 | Perform risk assessment on each contract based on regulatory updates | 2025-11-20 | 2025-11-21 | Thumma Joseph Kumar | Coding | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T3-03 | Update contract if needed based on new regulatory updates | 2025-11-22 | 2025-11-26 | Thumma Joseph Kumar | Others | 3- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T4-01 | Integrate SMTP to send alert to owner regarding contract revision | 2025-11-27 | 2025-12-05 | Thumma Joseph Kumar | Coding | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Z-4-5 | T4-02 | Design ChatBot conversation flow for contract Q/A | 2025-12-06 | 2025-12-10 | Thumma Joseph Kumar | Coding | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Lack of Clarity on project requirements | Conduct detail discussion with Mentor
Sprint 1 | Day 6 | Lack of Clarity on project workflow | Conduct detail discussion with Mentor
Sprint 2 | Day 12 | Confusion about analysis report generation | Conduct detail discussion with Mentor
Sprint 2 | Day 20 | Confusion about contract updation | Conduct detail discussion with Mentor
Sprint 3 | Day 25 | Difficulty in regulatory updates tracking | Conduct detail discussion with Mentor
Sprint 3 | Day 30 | Confusion about contract revision | Conduct detail discussion with Mentor
Sprint 4 | Day 35 | Difficulty in SMTP integration | Conduct detail discussion with Mentor
Sprint 4 | Day 42 | Difficulty in chatbot integration | Conduct detail discussion with Mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-10-16 | 2025-11-04 | Thumma Joseph Kumar | Implementing comprehensive error handling for API failures | Skipping integration tests before committing | Daily code reviews and pair programming sessions | Established automated API monitoring with alert thresholds
2 | 2 | 2025-11-05 | 2025-11-12 | Thumma Joseph Kumar | Conducting pre-analysis validation of contract formats | Manual vector embedding verification processes | Maintaining detailed schema documentation with version control | Implemented automated embedding quality validation pipeline
3 | 3 | 2025-11-13 | 2025-11-26 | Thumma Joseph Kumar | Implementing regulatory webhook subscriptions for real-time updates | Assuming static compliance rules without version tracking | Maintaining changelog of all regulatory amendments | Created automated version comparison and impact assessment tool
4 | 4 | 2025-11-27 | 2025-12-10 | Thumma Joseph Kumar | Implementing multi-channel notification fallback strategies | Hardcoding email templates without localization | Documenting all conversational flows and edge cases | Developed A/B testing framework for ChatBot prompt optimization